## Desired Behaviors
LiveMind Scrum Capability Assessment & Maturity Model
|  | Doing Agile (Shu) |  |  |  | Thinking Agile (Ha) |  |  |  | Being Agile (Ri) |  | Score by Topic
People | Roles | Development Team | No | Cross-functional | No | Self-organizing | No | Self-managing | No | Empowered | No | 0 | 0% | 0%
|  | Product Owner | No | Sufficiently engaged | No | One person | No | Defines the "what" | No | Accountable | No | 0 | 0%
|  | Scrum Master | No | Facilitator | No | Servant leader | No | Mentor | No | Coach | No | 0 | 0%
|  | Leadership | No | Conforming | No | Supporting | No | Promoting | No | Transforming | No | 0 | 0%
|  | < 9 Team Members | No | Co-located | No | Feature-based | No | Swarming | No | Generalized Specialists | No | 0 | 0%
Process | Artifacts | Product Backlog | No | Single Source of Requirements | No | Ordered List | No | Estimated | No | Emergent & Dynamic | No | 0 | 0% | 0%
|  | Sprint Backlog | No | Sprint Goal | No | Detailed Plan | No | Updated Daily | No | Highly Visible | No | 0 | 0%
|  | Burndown Chart | No | Velocity | No | Capacity | No | Release Burnup Chart | No | Additional Metrics | No | 0 | 0%
|  | Product Backlog Items | No | Specification by language | No | User Story | No | Specification by model | No | Specification by example | No | 0 | 0%
| Events | Release Planning | No | Timebox of 3 days or less | No | Scrum Team/Stakeholders | No | Results in 3 to 9 month roadmap | No | Achievable/Realistic | No | 0 | 0% | 0%
|  | The Sprint | No | Timebox of 2 weeks or less | No | Cadence | No | Results in "Done" Increment | No | Working Software | No | 0 | 0%
|  | Sprint Planning | No | Timebox of 8 hours or less | No | Scrum Team | No | Results in a Sprint Plan | No | Meets commitments | No | 0 | 0%
|  | Daily Scrum | No | Timebox of 15 minutes or less | No | Development Team | No | Results in a Daily Plan | No | Synchronized efforts | No | 0 | 0%
|  | Sprint Review | No | Timebox of 4 hours or less | No | Scrum Team/Stakeholders | No | Results in feedback | No | Collaborative | No | 0 | 0%
|  | Sprint Retrospective | No | Timebox of 3 hours or less | No | Scrum Team | No | Results in plan for improvement | No | Avoids 5 Dysfunctions | No | 0 | 0%
|  | Refinement | No | Continuous/Ongoing | No | Scrum Team/Stakeholders | No | 1 to 2 Sprints ahead | No | Just-in-time dissagregation | No | 0 | 0%
Tools | Technical Practices | Source code repository | No | Versioned code | No | Frequent checkins | No | Refactoring | No | Collective Code Ownership | No | 0 | 0% | 0%
|  | Build server | No | Scripted builds | No | Scheduled builds (daily) | No | On demand builds | No | Checkin triggered builds | No | 0 | 0%
|  | Testing | No | Quadrant 1 | No | Quadrant 2 | No | Quadrant 3 | No | Quadrant 4 | No | 0 | 0%
|  | Definition of Done | No | Acceptance Criteria | No | Test-Driven Development | No | Acceptance TDD | No | Behavior Driven Development | No | 0 | 0%
|  | Deployment scripts | No | Continuous Integration | No | Continuous Delivery | No | Continuous Deployment | No | DevOps | No | 0 | 0%
Responses |  | "Yes" | 0 | "Yes" | 0 | "Yes" | 0 | "Yes" | 0 | "Yes" | 0
|  | out of | 21 | out of | 21 | out of | 21 | out of | 21 | out of | 21
|  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
|  | 0% |  |  |  | 0% |  |  |  | 0%
www.LiveMindLLC.com